## Status
Deliverable | Date | Status (%)
A. Functional OpenMSE bag limit extension | 1st April 2023 | 100
B. Report documenting application to California Halibut | 1st May 2023 | 40
C. Report documenting application to second species | 1st July 2023 | 25
D. Draft Report | 1st August 2023 | 0
E. Final Report | 30th September 2023 | 0

## Tasks
Task | Status (%)
A. Examine and analyze the CDFW recreational catch data for California halibut and one other case-study to calculate probability of catching or exceeding the bag limit at a given stock size. | 50
B. Develop and describe the mathematical model used to calculate the impact of bag limits on the fishery dynamics, accounting for discard mortality and individual and boat bag limits and add to the openMSE framework as a management option that can be used in combination with other existing management options (e.g., TAC, TAE, etc.). | 50
C. Apply the bag limit feature to California halibut and one other case-study (e.g., groundfish species) identified by CDFW collaborators. | 40
D. Incorporate feedback from CDFW and other collaborators on technical documents and produce final project report. | 0
E. Provide co-authorship support for drafting CDFW scientists-led manuscript describing the methods and results of the application to the case-studies. | 0

## ATD
Priority | To Do
1 | Obtain location covariate data for Recfin catch rate observations to disaggregate data according to bag limits (e.g. SoCal Halibut is 5, NoCal Halibut is 3)
1 | Organize call to present work so far and get feedback on modelling
1 | Reach out to r4SS developers to understand which version is needed to read the lastest assessments
1 | Identify any missing regulations that need to be modelled (e.g. boat limits)
2 | In consultation with CDFW, identify a suitable second species (recfin data, regulation data, assessment model available) and arrange transfer of assessment files
2 | Convert halibut model to openMSE multi-OM (current demonstration is using an older generic openMSE OM to 2016 that does not include sex or fleet structure).
2 | Undertake data analysis for second species to fit discarding model